## Task Progress
ID | Phase | Task / Deliverable | Responsible Role | Start | Finish | Status | % Complete | Evidence / Notes
1 | Phase 1 | Stakeholder and organisation identified | Project Lead | 2026-08-03 | 2026-08-03 | Completed | 100 | Documented in SRS.
2 | Phase 1 | Stakeholder interview and requirements confirmation | Project Team + Stakeholder | 2026-08-21 | 2026-08-21 | Completed | 100 | Interview documented; requirements confirmed 21 August 2026.
3 | Phase 1 | Current process, users and problems documented | Requirements Lead | 2026-08-21 | 2026-08-22 | Completed | 100 | SRS Sections 2–3.
4 | Phase 1 | Stakeholder needs documented | Requirements Lead | 2026-08-21 | 2026-08-22 | Completed | 100 | SRS Section 6.
5 | Phase 1 | Functional requirements completed | Requirements Team | 2026-08-22 | 2026-08-23 | Completed | 100 | FR1–FR11 in SRS.
6 | Phase 1 | Non-functional requirements completed | Requirements Team | 2026-08-23 | 2026-08-23 | Completed | 100 | NFR1–NFR6 in SRS.
7 | Phase 1 | Integration requirements completed | Technical Lead | 2026-08-23 | 2026-08-23 | Completed | 100 | Flutter, ASP.NET and Supabase integration documented.
8 | Phase 1 | Requirements change log and refined scope | Project Lead | 2026-08-24 | 2026-08-24 | Completed | 100 | Microvet integration excluded; refined scope documented.
9 | Phase 1 | Feasibility study completed | Project Team | 2026-08-23 | 2026-08-25 | Completed | 100 | Six feasibility areas and overall decision documented.
10 | Phase 1 | Project risk register completed | Project Team | 2026-08-25 | 2026-08-25 | Completed | 100 | 10 risks and three highest risks documented.
11 | Phase 1 | SRS consolidated and reviewed | Documentation Lead | 2026-08-25 | 2026-08-25 | Completed | 100 | Unit 1 and Unit 2 work combined.
12 | Phase 1 | Stakeholder evidence compiled | Requirements Lead | 2026-08-30 | 2026-08-30 | Cpmpleted | 100 | Actual supporting evidence still needs to be attached/compiled.
13 | Project Management | GitHub repository checked and organised | Dev Lead | 2026-08-30 | 2026-08-30 | Completed | 100 | Verify README, activity and removal of confidential information/credentials.
14 | Project Management | Project Progress Tracker completed | Project Lead | 2026-08-30 | 2026-08-30 | In Progress | 50 | This workbook; replace member placeholders and confirm actual contributions.
15 | System Design | System architecture design | Technical Lead | 2026-08-24 | 2026-08-24 | In Progress | 50 | No design evidence supplied in source documents.
16 | System Design | Supabase database schema and roles | Backend Lead | 2026-08-25 | 2026-08-26 | In Progress | 50 | No implementation evidence supplied.
17 | Development | Flutter mobile application | Flutter Team | 2026-08-25 | 2026-08-29 | Not Started | 0 | No implementation evidence supplied.
18 | Development | ASP.NET web application | ASP.NET Team | 2026-08-25 | 2026-08-29 | Not Started | 0 | No implementation evidence supplied.
19 | Development | Supabase integration | Backend + Integration Team | 2026-08-28 | 2026-08-29 | Not Started | 0 | No implementation evidence supplied.
20 | Testing | Functional, security and consistency testing | Testing Team | 2026-08-28 | 2026-08-30 | Not Started | 0 | No test evidence supplied.
21 | Submission | Final SRS PDF and submission package | Documentation + Project Lead | 2026-08-31 | 2026-08-31 | Cpmpleted | 100 | SRS PDF, Project file, tracker, GitHub and stakeholder evidence.
22 | Presentation | Phase 1 presentation and defence preparation | All Group Members | 2026-08-31 | 2026-08-31 | Completed | 100 | All members must understand the complete project.
22 | Presentation | Phase 1 complete presentation | All Group Members | 03/09/2026 | 03/08/2026 | Completed | 100 | All members preseneted and concluded Phase 1
23 | Group Meeting | Group meeting for preparation of Phase 2 | All Group Members | 08/09/2026 | 08/09/2026 | Completed | 100 | All members met and communicated on how we are to tackle the Phase 2 requirements
24 | Group Consultation | Activity 3.1 consultation with Mr Mokoduwe | All Group Members excluding Mr Hlokoane | 10/09/2026 | 10/09/2026 | Completed | 100 | We made enquiries regarding unit three and Mr Mokoduwe suggested that when starting with development, we should start first with developing flutter application for pet owners and ASP.NET for staff members instead of using both of them.
25 | Group Meeting | Activity 3.2 and 3.3 | All Group Members excluding Mr Hlokoane | 10/09/2026 | 10/09/2026 | In Progress | 50 | We met and start with Activity 3.2 and 3.3

## Individual Contributions
Member Name | Assigned Role | Contribution / Responsibility | Evidence | Status | % Contribution
REPLACE WITH MEMBER NAME | Project Lead | Coordinate planning, requirements baseline, risk register and submission. | SRS; Project plan; tracker | Completed
REPLACE WITH MEMBER NAME | Requirements Lead | Stakeholder needs, requirements and stakeholder evidence. | SRS Sections 6–8; interview evidence | Completed
REPLACE WITH MEMBER NAME | Technical / Dev Lead | Technical feasibility, integration and GitHub coordination. | SRS; GitHub | Completed
REPLACE WITH MEMBER NAME | Flutter Developer | Mobile app and client booking functionality. | GitHub commits; screenshots; tests | Planned / Ongoing
REPLACE WITH MEMBER NAME | ASP.NET Developer | Staff web application and booking management. | GitHub commits; screenshots; tests | Planned / Ongoing
REPLACE WITH MEMBER NAME | Backend / Supabase Developer | Database, authentication, roles and integration. | Supabase; GitHub; tests | Planned / Ongoing
REPLACE WITH MEMBER NAME | UI/UX / Testing Lead | Usability, interface and testing/corrections. | Design files; test cases; defect log | Planned / Ongoing

## Stakeholder Engagement
Date | Activity | Participants | Purpose | Outcome / Requirements Confirmed | Evidence | Follow-up Action
2026-08-21 | Stakeholder interview | Dr. Nicolene Greyling + Project Team | Confirm current process, problems, needs and requirements. | Confirmed client name/contact/address; patient name/breed/age; symptoms/reason; vets and receptionists need booking management and history access. | Interview preparation form / supporting evidence | Compile and attach appropriate stakeholder evidence.
2026-08-24 | Scope confirmation | Dr. Nicolene Greyling + Project Team | Confirm realistic scope after feasibility analysis. | Microvet integration, online payments and automated reminders excluded from current phase. | SRS Requirements Change Log | Keep refined scope controlled.

## Challenges & Actions
ID | Challenge / Risk | Impact | Action / Mitigation | Owner | Status
C1 | Limited experience integrating Flutter, ASP.NET and Supabase | Integration delays/inconsistent data | Early integration proof-of-concept and integration testing. | Dev Lead | Open
C2 | Stakeholder availability may be limited | Requirements may be misunderstood | Schedule check-ins and confirm requirements in writing. | Project Lead | Open
C3 | Scope creep | Could threaten semester schedule | Lock refined scope; move excluded features to future backlog. | Project Lead | Open
C4 | Insufficient testing time | Defects may remain | Build testing buffer; prioritise core booking tests. | Project Lead / Testing Lead | Open
C5 | Unauthorised access/exposure of client information | Legal/ethical consequences | Role-based access; no real stakeholder data in public GitHub. | Dev Lead | Open
C6 | Uneven contribution/member unavailability | Task delays | Track tasks and redistribute work if necessary. | Project Lead | Open
C7 | Supabase free-tier limitations | Development/testing interruptions | Monitor usage and optimise queries. | Dev Lead | Open
C8 | GitHub version conflicts/loss of work | Work may be lost | Feature branches and regular small commits. | Dev Lead | Open

## Phase Summary
Phase | Period | Completed Work | Outstanding Work | Status
Phase 1 – Planning & Requirements | August 2026 | Stakeholder/problem analysis; SRS; requirements; feasibility; risk register; refined scope. | Compile stakeholder evidence and final admin/submission artefacts. | Completed with outstanding items
Phase 2 – System Design | After Phase 1 | No implementation evidence supplied in source documents. | Architecture, database schema, UI and web design. | In Progress
Phase 3 – Development & Integration | After system design | No implementation evidence supplied. | Flutter, ASP.NET, Supabase and integration. | Not Started

## Phase 1 Reflection
Reflection Area | Group Reflection
What went well | The group established a clear real-world stakeholder problem and translated the stakeholder interview into a structured SRS. The scope was refined to keep the project realistic for the semester.
Stakeholder engagement | The 21 August 2026 interview confirmed client/patient information requirements and that vets and receptionists need booking management and history access.
Requirements learning | The group documented functional, non-functional and integration requirements and recorded important scope changes, including exclusion of Microvet integration.
Feasibility and risk learning | The group evaluated six feasibility areas and identified 10 project risks with mitigations and contingencies.
Challenges | Key identified challenges are integrating Flutter, ASP.NET and Supabase, maintaining stakeholder availability, controlling scope, protecting information and allowing enough testing time.
What needs improvement | Keep the Progress Tracker and Microsoft Project current, maintain GitHub evidence, compile stakeholder evidence, and ensure development remains aligned with the refined scope.
Next steps | Complete system design, implement Flutter/ASP.NET/Supabase, integrate the platforms, test core booking functionality, correct defects and prepare final submission/presentation.

## Submission Checklist
Requirement | Status | Action Needed
Updated SRS single PDF | Final check | Convert final DOCX to PDF and check consistency.
Editable Microsoft Project file | In Progress | Import supplied CSV into Microsoft Project and save as .mpp; update actual progress.
Project Progress Tracker Excel | In Progress | Use this workbook; replace member placeholders and confirm actual contributions.
GitHub repository | Not verified | Insert working link; verify README, documentation and activity; remove confidential information/credentials.
Stakeholder evidence | Needs compilation | Attach appropriate interview/confirmation evidence.
Phase 1 presentation | Not started | Prepare all group members to explain the complete project.